Appendix 3
Equality Action Plan 2018-2022
Year 2 Progress Report

Accessibility statement

Any request for the document in another format or language will be considered.

Please contact equality.unit@eani.org.uk

1.0	Introduction

This document sets out our progress against the year 2 actions we committed to undertake as part of the EA Equality Action Plan. The Equality Action Plan is aligned to the EA Strategic Plan 2017-2027. It covers a four year period (2018-2022).

The plan is a ‘live’ document and as such will be reviewed on an ongoing basis.

The actions in the plan are reflective of actions and commitments included in the Education Authority’s Strategic Plan and are a response to the EA Audit of Inequalities which can be found on at https://www.eani.org.uk/about-us/equality/audit-of-inequalities.

2.0	Who to contact

The person in our organisation who is responsible for making sure that the actions in this plan are taken forward is Cathy Lavery.

Contact details:

Name: 	Emma Patterson

Title: 		Equality & Diversity Manager

Telephone number: (028)90 564212

Email: 	emma.patterson@eani.org.uk

Annual Progress Report 2019-20
Equality Action Plan – Review end of Yr. 2

Access to Education

|  | Action | Progress Report | Status |
| --- | --- | --- | --- |
| 1.1. | The Education Authority will work with the voluntary sector to develop guidance for schools on supporting their transgender pupils and wider school community EA will support the launch of the guidelines by hosting a conference for school leaders and Governors to disseminate the guidelines The Education Authority will establish Peer Professional Networks which will bring together Principals to share and learn best practice in supporting transgender young people in schools | In October 2019, EA published non-statutory guidance for staff in schools and other educational settings on how to support transgender young people. This guidance aims to support schools to ensure that transgender young people feel safe, supported and included at school. (https://www.eani.org.uk/school-management/policies-and-guidance/supporting-transgender-young-people) Following engagement with the Practitioner Group of Principals and school leaders during the development of the guidance, the view was that a ‘soft’ launch would be more beneficial. The guidance was launched on the EA Website and the DE Permanent Secretary wrote to all school leaders informing them of its availability should they need it. There has been a delay with the development of the peer support network due to other competing priorities. This will be completed in Year 3. | Ongoing from Yr. 1 Completed Action removed Carried over to Y3 |
| 1.2. | The Education Authority through its school aged mothers programme will continue to support young mothers to engage with school and achieve a range of qualifications. | The aim of the School Age Mother’s programme is to maximise the opportunities for young women who are pregnant and parenting to continue in compulsory education and beyond, and by so doing enhance their educational attainment, opportunities for ongoing training and future employment. The SAM’s programme addresses the educational, health, social and personal needs of the young women drawing on EA support and other statutory and community resources. Social inclusion is promoted through the delivery of peer support and group work programmes. During 2019-20 a total of 94 young mothers were supported by this programme. The number of teenage mums being referred to the programme is reflective of the decrease in teenage pregnancy but the work has become more intense with service users experiencing complex issues that make their lives more challenging. The decrease in caseloads this year has enabled us to increase the intensity and frequency of individual and group work which has benefitted the young women .This has in turn improved the uptake of attendance at group sessions and the overall involvement and participation in the programme. Also it has helped maintain and strengthen relationships with family friends and peers. | Annually Yr. 2 Completed |
| 1.5. | The EA will conduct engagement with key stakeholders, including schools, parents, SENCos, young people, and key advocacy groups (CLC, HRC, NICCY), regarding arrangements for the new rights of children over compulsory school age EA will develop structures and processes to facilitate and support children over compulsory school age to exercise their rights. EA will develop guidance, including child friendly and easy read, to support schools and young people to participate in a meaningful way. EA will include guidance and support arrangements in EA officer, principal, SENCo, and BoG training programmes. | SEND Team consulted with CLC representatives in Jan 2020 regarding how EA should determine capacity of young people to exercise certain rights. SEND Team consulted with Educational Psychology Service, Transition team co-ordinator regarding proposed procedure for determining capacity. SEND Act 2016 - Children’s Disability Alliance DE/EA Transitions Project Team Engagement with SENCos, school principals, BoGs Briefing document drafted and circulated to Heads of Service, detailing proposal for EA and school management of processes in determining capacity. To be taken forward. Guidance drafted on rights of young people for school, parents, and the young person. Child friendly and Easy Read versions drafted. Seeking the views of the child booklet shared with schools and EA Services. Notes of guidance contained within on how to support pupil voice and participation in contributing to statutory assessment/ annual review/transition plan. SEND Act 2016 - Children’s Disability Alliance DE/EA Transitions Project Team Engagement with SENCos, school principals, BoGs | Complete Jan 2020 Complete Feb 2020 18/19 19/20 (ongoing) 19/20 Feb 20 - Ongoing March – June 20 Ongoing, awaiting DE Ongoing –awaiting approval/ DE & EA processes to be agreed and in situ. Completed 19/20 Completed and will be ongoing |
| 1.6. | EA will develop an accessible information policy and database to capture decisions | There has been some delay in this action due to consideration of recommendations arising from the New Decade New Approach report. It is envisaged that a policy will be drafted and consulted upon during Year 3 and a database developed thereafter. | Year 2 Carried over to Y3 |
| 1.8. | EA will develop a corporate framework around consultation which represents our values of Openness and Transparency | The purpose of the framework is to support officers in delivering the highest level of open and transparent consultation across EA in a consistent way. It will support officers in identifying the correct audiences to engage with based on the subject area, to think about the most effective methods of engagement and standardise how we approach engagement. The framework was launched during November 2019 and it is anticipated for associated training to take place during 2020.21. | Year 2 Completed |
| 1.10. | EA will develop a new website that is accessible for all our service users. EA will self-audit the accessibility of its website. | EA are continually working to ensure the existing website meets accessibility requirements. Regarding development of a new EA website, the aim is that this is due to be in place for September 2021. Service user feedback was obtained in the latter part of 2019 via the Staff Disability Network “EA Link” regarding accessibility of the current website. Changes have been made resulting in a new accessibility tool being rolled out, namely; ‘Recite me’. | Year 2 Carried over to Y3 Complete |
| 1.11 | EA will identify service areas to pilot the socio – economic assessment | Service areas have been identified and the pilot questions will be included in selected service area equality screenings in Year 3 to assess its impact. During the year, we also took the opportunity to work directly with relevant service areas to progress socio economic rights such as with Free School Meals/ Uniform Allowance to ensure an improved uptake and knowledge of how to apply for disadvantaged groups. | Year 2 Completed |

Attainment

|  | Action | Progress Report | Status |
| --- | --- | --- | --- |
| 2.1 | - Complete the Strategic Review of Nursery Provision in Special Schools and develop an Action Plan for implementation - Roll out a training programme for Principals and Boards of Governors regarding the SEND Act 2016 - Develop actions for supporting early intervention through the joint Education/Health Working Group for Early Years SEN Provision - Provide support to children with diabetes through an agreed health/education protocol Deliver the Facilitating Life and Resilience Education (FLARE) Mental Health project in in partnership with the Public Health Agency | In March 2018, EA launched a public consultation on a proposed framework of future educational provision for children in the early years with special educational needs (SEN) in Northern Ireland. In addition to the draft proposals contained in the framework, EA also consulted on a draft EQIA. 269 responses were received. A final EQIA has been completed and a final Summary of Consultation and associated framework/business case is in development for consideration by the EA Board. It is likely that this will progress during the 2020/21 year. SEND Act Awareness raising for Principals & BoG SEND Act – SEN Categories for Principals & BoG SEND Act - roles and responsibilities within the new SEN framework & to inform the quality assurance role of the Board of Governors in overseeing SEN Provision and in supporting pupils with special educational needs. Above will continue in the form of online training from Sept/Oct 2020 as training suspended 19/20 due to pandemic. From February 2021 training on the new PLP will be rolled out. Training schedule being compiled. The SEN Early Years Inclusion Service (SENEYIS), Getting Ready to Learn (GRtL), The Early Years Panel (EYP), and the Pre-school Education Group (PEG) are working in collaboration with one another under the leadership of the Head of Early Years to build on the work of the strategic Early Years Joint Health Education Working Group. Unfortunately some meetings had to be cancelled due to Covid-19. Significant work has been done by DE and EA on educational restart planning. It is hoped that the meetings can be rescheduled and held either remotely or in keeping with PHA social distancing guidelines going forward. - A scoping exercise of all EA and Health linkage within Early Years Services has been conducted. - Co-operation is ongoing between EA Early Years Services and RISE NI to co-develop and co-deliver training. - In March 2019, PHA facilitated 6 members of staff from SEN EYIS in attending Level 1 Paediatric Continence Training with Bowel and Bladder UK. This allowed EYIS staff to train alongside HSCT colleagues in an area of common interest. - SEN EYIS staff were given the opportunity in September 2019 to contribute to a draft Continence Guidance Document for schools being developed by Bowel and Bladder UK to ensure that setting and school messages were aligned and appropriately targeted. - Through links with PHA, there has been contact between SEN EYIS and GRtL staff to develop strategic links with Health Visiting. - SEN EYIS staff attend West Belfast Partnership Board, contributing to the development of resources for nurseries and schools. - Established links between SEN EYIS staff and HSCT colleagues in Paediatrics and with AHPs are on-going. This includes the strand of EYIS support which involves outreach staff from Special Schools who receive cases at regular triage meetings and provide support on behalf of EA. - Arrangements are in place for Community Paediatricians to refer pre-pre-school children with complex needs to the Interim Early Years Panel. - The Interim Early Years SEN Panel provides feedback to Paediatricians and parents who make referrals to the Panel. - Representative Senior Early Years Social Workers from all HSCTs sit on the EA Preschool Education Group. There are excellent working relationships and good reciprocal communication has been developed. - There is also a single Child Care Partnership representative on PEG on behalf of all HSCTs. - The PEG Regional Co-ordinator sits on the Western Child Care Partnership where excellent 2 way collaboration/communication has been established. The Booklet ‘Diabetes Care: What care to expect in schools’ has been updated in collaboration with PHA. EA is awaiting a foreword from the PHA. A re-launch had been provisionally planned with Diabetes UK for June 2020 but necessarily postponed. A paper setting out joint Health Education arrangements is in draft form. It is intended that this paper once finalised will receive joint consideration by CYPS Committee and parallel Health governance structures. Liaison meetings have taken place between relevant EA staff and the Regional Paediatric Diabetic Nurse Specialist Group and PHA to discuss operational arrangements for appropriate support. Please note that this process has been paused due to key health staff involvement in the Covid-19 response. Operational arrangements for on-going support remain in place. FLARE is an EA led project funded by PHA. Its core aim is to reduce the stigma of mental health and support young people aged 11 – 25 yrs., through 1-2-1 work, group work and capacity building in NI. During the 2019-20 year 217 young people were referred into FLARE services and 145 young people were supported by FLARE. In addition a further 81 young people were signposted to FLARE services. | Years 1-4 Ongoing Ongoing 17/18 18/19 19/20 20/21 Years 1-4 Completed Years 1-4 Completed Years 1-4 Completed |

Bullying

|  | Action | Progress Report | Status |
| --- | --- | --- | --- |
| 3.1. | EA will develop and provide supplementary guidance to our schools on the roles of senior managers and governors in addressing bullying in schools EA will continue to support schools to meet the needs of individual pupils or groups, through the EA Behavioural Support Service. | In 2019, EA worked together with the Northern Ireland Anti-Bullying Forum (NIABF) to promote the reduction of bullying incidents in school, and to support schools and families should incidents occur. In February 2020 the NIABF hosted the first ever Northern Ireland Anti-Bullying Young People’s Forum. It was held on 7th February at Parliament Buildings when 100 young people aged between 15 and 19 and from schools and colleges across Northern Ireland came together to consider a range of issues related to bullying. All training materials for schools and Governors can be found at: https://www.eani.org.uk/school-management/policies/addressing-bullying-in-schools-act-2016 EA staff are currently continuing to engage with schools through their Area Learning Communities to offer further support to enable schools to be prepared for the commencement of the Act. After the commencement of the Act, EA will continue to support schools with policy development, Effective Responses to Bullying Behaviour training and individual school support and training through the Behaviour Support and Provisions training programme for schools. The Department of Education issued a ‘pause’ on the commencement of the Act in September 2019 due to issues raised by the Unions. DE, EA, NIABF and NAHT met to discuss issues and find solutions to move forward. Changes to the Guidance were completed by DE. At this stage we are awaiting confirmation of a commencement date. | Year 2 Ongoing |
| 3.2. | With the support of the Anti-Bullying Forum, EA will develop an anti-bullying campaign across our schools, including principal and Boards of Governor training, to develop a strong and visible anti-bullying culture in schools | The Department of Education issued a ‘pause’ on the commencement of the Act in September 2019 due to issues raised by the Unions. DE, EA, NIABF and NAHT met to discuss issues and find solutions to move forward. Changes to the Guidance were completed by DE. At this stage we are awaiting confirmation of a commencement date. | Education CYPS Equality Yr. 2 Carried over to Y3 |

Data

|  | Action | Progress Report | Status |
| --- | --- | --- | --- |
| 4.2. | EA will annually publish the Intercultural Education Service Delivery Plan | The Intercultural Education Service (IES) Delivery Plan has been shared with DE and the Equality Commission and data is now available for EA staff to assess and benchmark. The plan for 2020-21 is currently being finalised. | Carried over to Y3 |
| 4.3. | Research will be carried out into the needs of young people with additional needs Research will be carried out into the needs of young carers Research will be carried out into the needs of young parents | EA Regional Youth Development Plan for 2020 - 2023 outlines the key targets to be achieved by EA Youth Service, based on the 3 year Regional Assessment of Need 2020- 2023 and in accordance with the DE Policy. Since April 2019 the Youth Service has engaged in 12 stakeholder events on a range of six themes relevant to the needs of young people, carried out in-depth desktop research and completed their largest online survey to consult with young people with over 16,000 responses. Whilst the comprehensive Regional Assessment of Needs was completed, specific research into young people with additional needs and young carers has yet to commence. These will be carried over to Year 3 actions. Research into the needs of young parents has commenced, however this is still ongoing. | Carried over to Y3 Ongoing, to be published in Y3 |

Emotional Health and Wellbeing

|  | Action | Progress Report | Status |
| --- | --- | --- | --- |
| 5.2. | EA will establish a pilot scheme for the “Schools of Sanctuary” programme. | The 14 schools who commenced the School of Sanctuary programme in September 2018 completed their portfolios by the end of June 2019 and held a joint celebration of their achievements during Good Relations week on the 16th September 2019. In September 2019, 14 more schools in Belfast, Lisburn (Colin Area) and Derry/Londonderry began their journey on a new School of Sanctuary programme and prepared varied action plans which incorporated a CRIS Buddy up programme and a Creative Arts Programme. | Year 1 – 3 Target was 10 schools per year, over the next 3 years. Result is that 14 schools per year have become Schools of Sanctuary. Completed |
| 5.3. | EA will support vulnerable children and young people following the death of a pupil or member of the school through the Critical Incident Response Team | The number of schools supported by EA as a result of a Critical Incident in the period April 2019 – March 2020 was 56. The Critical Incident Support Service continues to provide: - EA Critical Incident Response Team (CIRT) Regional Helpline Support (028 3751 2515) - Monitoring of the Helpline during and out of office hours - EA CIRT information on the EA website - Regional Capacity Building Training for School Staff in relation to Bereavement and Critical Incident Management - Contribution to the New Principals training programme | Annually Completed |
| 5.4. | EA will continue to manage, support and develop the 31 Nurturing Schools in NI and develop a Nurturing Framework to support all schools to develop a Nurturing Environment, supporting the Emotional Health and Wellbeing of their pupils | 31 DE Funded Nurture Groups established in Primary Schools in NI 31 DE Funded Nurture Groups managed and supported by the Nurturing Approaches in Schools Service through operational visits, support meetings with Nurture Staff, Steering Group Meetings, Area Clusters, Farouk Clusters – with Education Psychology support, Principal Clusters, Bespoke Whole School Training, Cluster Training for Nurture Staff. 601 children identified via Boxall Profile and supported through 31 Nurture Groups. - 114 were Child Looked After (CLA). - 332 children have returned to their mainstream class by February 2020. 2104 additional children were supported through social group’s / crisis management / Key Stage 2 groups. 151 school staff (teaching & non-teaching) participated in Continued Professional Development (CPD) training in the following; - 31 – “Whole School Nurture Approach” model of support - 51 - Theraplay – activities to build attachment - 41 - Emotional health strategies & techniques - 28 – Coventry Grid 20 nurture group staff participated in CPD through the modelling of interventions with 153 pupils in their nurture group. 55 clusters of support were facilitated with 31 Schools involved in professional collaboration / sharing of best practice and the Farouk Problem Solving Model in conjunction with Psychology Service. 2019 -2020 further implementation of the Whole School Nurturing Approaches Model of Support framework in line with DE guidance. 49 Primary Schools in receipt of Level 3 whole school Inset 57 schools in total have completed the WSNA Readiness Analysis and nurture action plan to strategically embed and direct nurturing approaches within the whole school community. 93 CPD follow up sessions with school staff (teaching & non-teaching) including modelling of pupil interventions. 918 staff (teaching & non-teaching) engaged in CPD including modelling of interventions. 1045 pupils participated in the modelling of interventions. 19 new schools registered to use the Boxall Profile assessment tool. 5 sessions of cross service / sector / multi-disciplinary collaboration with 170 professionals. Level 2 Conferences x 2 completed – Dec 2019 & Jan 2020 – 52 Primary Schools attended Level 3 expressions of interest opened – remain open due to Covid -19 Currently 10 expressions of interest. | Year 1-3 Completed |
| 5.5. | EA will undertake service reviews based on the feedback, and in consultation and engagement with schools | A Project Initiation Document (PID) was developed for the Review of Pupil Support Services. This project has not progressed following guidance from DE to carry out a base-lining exercise of all Pupil Support Services, which was completed in March 2020. | Year 1-4 Ongoing |
| 5.6. | EA will deliver personal development and resilience programmes to young people, in EOTAS provision, through a youth worker | EA Youth Service delivered personal development and resilience programmes to 420 young people, in 14 EOTAS centres. 18 Youth Workers delivered these programmes. | Year 2 Completed |
| 5.7. | EA will develop personal development and resilience programmes for young people in schools which will be delivered by the Youth Service. This work is in addition to the work that is carried out through the curriculum in schools | Youth Service currently delivering programmes for Year 11 and Year 12 in 50 schools across the region. (Learning Together). Youth Service also delivers a range of Transition and Key Stage 3 programmes | Years 1-4 Completed |

Workforce

|  | Action | Progress Report | Status |
| --- | --- | --- | --- |
| 6.1. | EA will develop a model for accurately measuring staff engagement | Consideration of methods to measure staff engagement began during Year 2 however progress has been limited due to lack of resources. It is planned, as part of ongoing work within OD&L, linking closely with Communications, to take methods of staff engagement forward in a more structured and regular manner during Year 3. It is envisaged this would include regular Staff Pulse surveys alongside other means of engaging with staff and obtaining feedback. | Year 2 Carried over to Y4 |
| 6.3. | Working with trade unions and other partners, EA will develop and deliver a gender action plan (GAP). We will report on this annually. | The development of a GAP was a commitment made in the Equality Action Plan 2018–2022 and was launched in September 2019. The GAP is values led and people centred; and is enabled by the corporate values of; openness, respect, reflection, responsibility, excellence and equality. The delivery and promotion of the GAP will result in positive outcomes on gender equality for EA whilst promoting diversity and inclusion in the workplace. The outworking of the plan is currently underway and will be reviewed annually. | Year 2 Completed |
| 6.4. | EA will establish a Staff Support Network for LGBT colleagues. The Authority will join Diversity Champions programme and seek to become a Stonewall Top 100 employer | The original EAP provided a timescale of establishing an LGBT+Friends staff network by Year 3, however this was completed earlier than planned during Year 2. During the year, the staff network “EA Gleam” has developed a Terms of Reference, a Chair and Vice Chair appointed an Activity Plan for 2020/21 developed and agreed. In addition, “EA Gleam” attended the Working with Pride Breakfast in August 2019. The decision was taken at the end of the 2019-20 financial year to pause membership of Diversity Champions and not renew membership for 2020-21 due to COVID19. EA have been members for two years and have utilised significant parts of the programme including the Workplace Equality Index, which has supported the delivery of diverse and inclusive workplace initiatives across the organisation. Following the delivery of the Staff Network’s action plans over the next two years, it is proposed to reassess Diversity Champions Membership at that stage, in line with the EAs new Equality Action Plan. | Year 2 Completed Action removed |
| 6.7. | EA will develop processes for encouraging more young people to apply and work for EA | EA attended Skills NI on 20 and 21 November 2019. EA profiled different parts of the organisation including Transport, Youth Service, Procurement and IT. This initiative supports the programme of work EA are planning for 2021-22 around engaging people to work in EA, specifically young people. It is planned to take forward in Year 3 the development of an EA Placement Scheme to include young people as one of priority groups. | Year 2 Completed |

| Equality action plans/measures |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Within the 2019-20 reporting period, please indicate the number of: |  |  |  |  |  |
| Actions completed: | 17 | Actions ongoing: | 7 | Actions to commence: | 7 |