Appendix 4
Disability Action Plan 2018-2022
Year 2 Progress Report

Accessibility statement

Any request for the document in another format or language will be considered.

Please contact equality.unit@eani.org.uk

1.0	Introduction

This document sets out our progress against the year 2 actions we committed to undertake as part of the EA Disability Action Plan. The Disability Action Plan is aligned to the EA Strategic Plan 2017-2027. It covers a four year period (2018-2022).

The plan is a ‘live’ document and as such will be reviewed on an ongoing basis.

The actions in the plan are reflective of actions and commitments included in the Education Authority’s Strategic Plan.

2.0	Who to contact

The person in our organisation who is responsible for making sure that the actions in this plan are taken forward is Cathy Lavery.

Contact details:

Name: 	Emma Patterson

Title: 		Equality & Diversity Manager

Telephone number: (028)90 564212

Email: 	emma.patterson@eani.org.uk

Progress Report Year 2 - Disability Action Plan

- Promoting positive attitudes towards disabled people

|  | Action | Progress Report | Status |
| --- | --- | --- | --- |
| 1.2. | We will host disability awareness days twice a year for staff and invite the community sector to participate | During the 2019-20 year, we celebrated two key dates. International Day of Persons with a Disability on the 3 December 2019. The newly established Disability and Carers Staff Network, EA Link, have been working through their Year 1 activity plan. Members of the network helped to raise awareness of disability and caring responsibilities, by organising and hosting a number of information events across EAs regional offices. Representatives from many community and voluntary organisations were available to provide advice and guidance. The event was shared and highlighted via social media posts on Facebook & Twitter, staff intranet and EA website. World Downs Syndrome Day on the 21 March 2020. Key messages around Downs Syndrome Day and Downs Syndrome was shared with staff across EA and in schools. Across social media the #LotsOfSocks hashtag and a corporate message of support was shared. | Year 2 Fully Achieved |
| 1.5. | EA will ensure staff are up to date with required disability related training, including on reasonable adjustments, and report on training undertaken each year | EA has signed up to Employers for Disability NI; an organisation who offers advice on disability related queries and issues for employers and employees. A new single support service for colleagues with a disability was established in March 2020 – the Disability Employment Support Service. This service will be responsible for developing training resources and line manager guidance. In the interim, throughout March 2020, they have provided detailed and bespoke advice and guidance to managers and colleagues. Further to this, as an integral part of the equality and diversity training and awareness programme, disability legislation and disability awareness is an integral part. 648 colleagues attended the training throughout the year. | Ongoing Fully Achieved |
| 1.6. | Will sign up to, adopt and implement the principles contained within the Mental Health Charter and associated work plans developed by the consortium of mental health organisations and the Equality Commission for Northern Ireland | Mental Health First Aid training has been delivered to 60 EA staff during the year and the Mental Health First Aiders initiative was formally launched on 10th October 2019 (World Mental Health Day). A package of ongoing training and support for MHFA is being developed. | Year 1-4 Fully Achieved |
| 1.9. | We will have a corporate approach to the use of images including photography in corporate publications, which re-enforces a positive image of people with disabilities accessing our services | This action will be carried over to the 2020 – 2021 business year to align with the corporate review of brand guidelines. | Not Achieved |
| 1.10. | We will ensure the new Human Resources system allows staff to easily and confidentially disclose their disability status | The specification for the new eaone system allows staff to indicate their disability status as a part of the self-service functionality of the system. Work is on-going to roll this system out. | Year 2 & Year 4 Fully Achieved |
| 1.11. | We will review the EA Sign Language Interpretation Service for deaf or hard of hearing parents and develop a new service. | The review of the EA Sign Language Interpretation Service for deaf /hard of hearing parents has been started. Some benchmarking on what other public authorities offer has been undertaken. The review will continue during 2020.21 with a view to developing a policy and support service during Year 3. | Year 2 Partially Achieved |

- Encouraging the participation of disabled people in public life

|  | Action | Progress Report | Status |
| --- | --- | --- | --- |
| 2.3. | Disability Issues will feature as part of the agenda of the Joint Consultative Forum | The Joint Consultative Forum (JCF) meeting of the 12 March 2020 was hosted on the theme of Special Educational Needs and Disability Education. The Board’s Disability Champion, Oliver McMullan hosted the meeting and welcomed the participants and presenters. The JCF agenda also included an update from the SEND Implementation Team on the CYPS SEND Implementation Plan. Participants had the opportunity to discuss EA Plans and contributed views on how they believed the service could be improved, including working together with occupational health therapists and parents, making information available earlier and providing adequate support in classrooms for young people. The Department of Education provided participants with an update on the SEN Learner Journey Project which aims to improve the use of technology, communication and practices. The Department outlined changes to communication with parents, the development of an ‘App’ for parents to monitor their child’s progress and how they are improving the role of the SENCO. | Ongoing Fully Achieved |
| 2.5. | We will develop a new website that meets the required accessibility standards We will self-audit the accessibility of our website | EA are continually working to ensure the existing website meets accessibility requirements. Regarding development of a new EA website, the aim is that this is due to be in place for September 2021. A self-audit with the Disability Staff Network “EA Link” and ICT was carried out during December 2019. Changes have been made to the accessibility tool being utilised and it is now ‘Recite me’. | Year 2 Not Achieved Fully Achieved |
| 2.6. | We will develop an accessible information policy and database to capture decisions | Due to resource issues, this has not been achieved. This action will be delivered by Year 4 of the Action Plan. | Year 2 Not achieved |
| 2.9. | We will attend careers fairs and promote EA as a Disability Friendly Employer | EA attended Skills NI on 20 and 21 November 2019 profiling different parts of the organisation including Transport, Youth Service, Purchasing and IT, with staff on hand to discuss a future career at EA with the young people in attendance. The event, which is aimed at 14-19 year olds, their teachers, parents and influencers, helps young people decide how to achieve their career path. This initiative supports the programme of work EA are planning for 2021-22 around engaging people to work in EA, specifically young people, people with disabilities and the long term unemployed. It is planned to take forward in Year 3 the development of an EA Placement Scheme to include people with disabilities as one of priority groups. | Year 2 Onwards Fully Achieved |
| 2.10. | Reasonable Adjustments Policy will be developed to include the financial considerations, training and practical steps in improving accessibility | A single point of contact, the Disability Employment Support Team was established in March 2020. One of the key activities for this team will be to draft policy and guidance for managers on managing reasonable adjustments. Further work on this was delayed due to Covid-19. Anticipated to continue at pace during 2020.21. | Year 2 Partially Achieved |
| 2.11. | We will be a model employer for colleagues with a disability | EA signed up to Employers for Disability NI in August 2018 and continues to work closely with them in supporting colleagues with a disability. | Year 1-4 Fully Achieved |

PART B - Section 49A of the Disability Discrimination Act 1995 (as amended) and Disability Action Plans

| 1. Number of action measures for this reporting period that have been: |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8 |  |  |  | 2 |  |  |  | 3 |  |  |  |
| Fully achieved |  |  |  | Partially achieved |  |  |  | Not achieved |  |  |  |